## Project Details
Infrastructure Investment Plan - Project Pipeline (as of 31 August 2016) - [Notes 1, 2]
Project Sector | Project Name | Project Description | Project Type | Public Sector Procurement Body | Total Capital Investment (£) [Notes 3,4,5,6] | How is the project being Funded? [Note 7] | Procurement Route | Current Project Status [Note 8] | Project Advertised to Market [Note 9] |  | Construction Start [Note 9] |  | Operational/Service Start [Note 9] |  | Contact For Public Enquiries Name | Contact For Public Enquiries Email [Note 10]
[9 empty] | Status | Date | Status | Date | Status | Date
Transport | M8 M73 M74 Motorway Improvements Project | This project will complete the Central Scotland motorway network, with benefits including reduced congestion and safer, quicker journeys. | Road | TRANSPORT SCOTLAND | 439,000,000 (revenue funded element: 310,000,000) | Revenue Funded | NPD (Non Profit Distributing) | In Construction | Completed | 30/03/2012 | Completed | 20/02/2014 | Planned | 30/04/2017 | Transport Scotland | info@transport.gov.scot
Transport | Forth Replacement Crossing | The Forth Replacement Crossing project is necessary to ensure that there is an effective replacement of the existing functionality of the Forth Road Bridge in regard to general traffic. The project also maintains the use of the Forth Road Bridge as part of a public transport corridor. | Road | TRANSPORT SCOTLAND | 1,325,000,000 - 1,350,000,000 | Capital Funded | Conventional Capital Procurement | In Construction | Completed | 26/06/2009 | Completed | 28/06/2011 | Planned | 31/05/2017 | Transport Scotland | info@transport.gov.scot
Transport | Edinburgh Glasgow Improvement Programme EGIP | A comprehensive programme of improvements to Scotland’s railway infrastructure, rolling stock and service provision that provides a major boost to the wealth of Scotland and its long term economic sustainability. | Rail | TRANSPORT SCOTLAND | 742,000,000 (RAB funded value: 714,000,000) | Revenue funded | RAB (Regulatory Asset Base) | In Construction | Completed | 28/06/2011 | Completed | 04/01/2012 | Planned | 31/03/2019 | David Ray | David.Ray@transport.gov.scot
Transport | A77 Maybole Bypass | The project involves the construction of a new off-line bypass approximately 5km in length to the west of the town of Maybole | Road | TRANSPORT SCOTLAND | 43000000 | Capital Funded | Conventional Capital Procurement | In Preparation | Planned | 30/08/2017 | Planned | 15/08/2018 | Planned | 15/02/2020 | Transport Scotland | info@transport.gov.scot
Transport | A737 Dalry Bypass | The project involves the construction of a new off-line bypass approximately 3.7km in length to the east of the town of Dalry. | Road | TRANSPORT SCOTLAND | 58900000 | Capital Funded | Conventional Capital Procurement | Invitation to Tender Issued’ | Completed | 22/03/2016 | Planned | 2017-03-21 | Planned | 2018-09-17 | Transport Scotland | info@transport.gov.scot
Transport | A90/A96 Haudagain Junction Improvement | Improvements to the A90/A96 Haudagain Roundabout to reduce congestion and improve journey time reliability. | Road | TRANSPORT SCOTLAND | To be confirmed [Note 11] | Capital Funded | Conventional Capital Procurement | In Preparation | Planned | 17/03/2017 | Planned | 31/03/2018 | Planned | 31/03/2019 | Transport Scotland | info@transport.gov.scot
Transport | A90 Aberdeen Western Peripheral Route/Balmedie-Tipperty | The A90 Aberdeen Western Peripheral Route (AWPR) is being delivered alongside the A90 Balmedie-Tipperty scheme through a single NPD contract. There are two major constitution elements, the 46km AWPR and the 9.5km A90 Balmedie-Tipperty. | Road | TRANSPORT SCOTLAND | 745,000,000 (revenue funded element: 469,000,000) | Revenue Funded | NPD (Non Profit Distributing) | In Construction | Completed | 18/01/2013 | Completed | 12/12/2014 | Planned | 31/12/2017 | Transport Scotland | info@transport.gov.scot
Transport | A9 Dualling: Kincraig to Dalraddy | The first stretch of the A9 dualling programme comprising a 7.5km stretch of dual carriageway to the south of Aviemore. | Road | TRANSPORT SCOTLAND | 45000000 | Capital Funded | Conventional Capital Procurement | In Construction | Completed | 19/08/2014 | Completed | 30/06/2015 | Planned | 30/06/2017 | Transport Scotland | info@transport.gov.scot
Transport | CMAL - Two new 100 metre ferries | CMAL - Two new 100 metre ferries. The ferries are being designed to provide year round service to the Isle of Arran and the Uig Triangle. (Uig - Tarbert - Lochmaddy). | Ferry | CALEDONIAN MARITIME ASSETS LTD | 97000000 | Capital Funded | Conventional Capital Procurement | In Construction | Completed | 15/10/2014 | Completed | 15/12/2015 | Planned | 01/07/2018 | Bob Davie | bob.davie@transport.gov.scot
Transport | Stirling Dunblane Alloa Rail Electrification (SDA) | Project involves electrification of 100 single track km of track from Dunblane through Stirling and Alloa connecting to the newly electrified Edinburgh - Glasgow via Falkirk high route at Larbert. The project includes £13 million advance route clearance works to prepare the route for electrification. | Rail | TRANSPORT SCOTLAND | 92,000,000 - 159,000,000 | Revenue funded | RAB (Regulatory Asset Base) | Tender Evaluation | Completed | 28/06/2011 | Planned | 04/10/2016 | Planned | 02/12/2018 | David Ray | David.Ray@transport.gov.scot
Transport | Aberdeen to Inverness Improvement Project | A phased package of improvements to the railway line between Aberdeen and Inverness to reduce journey times, improve infrastructure, connectivity and capacity on an incremental basis by 2030. | Rail | TRANSPORT SCOTLAND | 170,000,000 - 283,000,000 | Revenue funded | RAB (Regulatory Asset Base) | In Preparation | Planned | 23/12/2016 | Planned | 08/01/2017 | Planned | 30/09/2019 | Anne Armstrong | anne.armstrong@transport.gov.scot
Health | Building For Better Care | Redesign 'Front Door' by enhancing level of Accident & Emergency Services delivered by Consultants in Emergency Medicine at Ayr and Crosshouse Hospitals to provide single point of access to A&E, Minor Injury and Illness Service, and, Ayrshire Doctors On Call Service. | Hospital (Refurbishment/Development) | NHS AYRSHIRE & ARRAN | 27600000 | Capital Funded | Framework | In Construction | n/a | n/a | Completed | 19/05/2014 | Planned | 30/04/2017 | John Wright | john.wright@aapct.scot.nhs.uk
Health | Acute Services Redevelopment Project | Replacement of Dumfries and Galloway Royal Infirmary to facilitate the provision of services in a high quality environment which is fit for purpose for staff, patients and visitors. | Hospital (New Build) | NHS DUMFRIES & GALLOWAY | 275,500,000 (revenue funded element: 212,600,000) | Revenue Funded | NPD (Non Profit Distributing) | In Construction | Completed | 25/06/2013 | Completed | 12/03/2015 | Planned | 01/12/2017 | Susan McMeckan | susan.mcmeckan@nhs.net
Health | NHS Orkney New Hospital and Healthcare Facilities | The project will provide a new integrated Rural General Hospital including 2 primary care practices and public dental services with SAS and NHS24 co-located on the site. | Hospital (New Build) | NHS ORKNEY BOARD | 67,500,000 (revenue funded element 59,000,000) | Revenue funded | NPD (Non Profit Distributing) | Preferred Bidder Appointed | Completed | 17/07/2014 | Planned | 2016-12-31 | Planned | 2019-02-28 | Ann Mccarlie | ann.mccarlie@nhs.net
Health | NHS Scotland Pharmaceutical Specials Service | Access to Unlicensed Medicines in NHS Scotland | Community Services | NHS TAYSIDE | 28,600,000 (revenue funded element: 25,400,000) | Revenue funded | Hub | In hub Development | n/a | n/a | Planned | 21/10/2016 | Planned | 09/10/2018 | Lesley Henderson | pss.tayside@nhs.net
Health | Scottish National Blood Transfusion Service National Centre | Consolidation of SNBTS Blood Processing & Testing, Tissues and Cells and other SNBTS functions onto a single site in the Central Belt | Hospital (New Build) | NHS NATIONAL SERVICES SCOTLAND | 38,100,000 (revenue funded element: 33,300,000) | Revenue Funded | NPD (Non Profit Distributing) | In Construction | Completed | 23/10/2012 | Completed | 13/10/2014 | Planned | 31/03/2017 | Amelia Whittaker | amelia.whittaker@nhs.net
Health | Royal Hospital for Sick Children / Department of Clinical Neurosciences | A project to re-provide services from the Royal Hospital for Sick Children, Child and Adolescent Mental Health Service and the Department of Clinical Neurosciences in a single building adjoining the Royal Infirmary of Edinburgh at Little France. | Hospital (New Build) | NHS LOTHIAN | 230,100,000 (revenue funded element: 150,000,000) | Revenue Funded | NPD (Non Profit Distributing) | In Construction | Completed | 05/12/2012 | Completed | 16/02/2015 | Planned | 2018-04-01 | Brian Currie | RHSCandDCN@nhslothian.scot.nhs.uk
Health | Redesign of Mental Health Facilities Argyll & Bute | Transfer of Mental Health services from hospital to community and provision of modern in patient facilities for those patients who still require hospital care. | Hospital (New Build) | NHS HIGHLAND | To be confirmed [Note 12] | Revenue funded | Hub | In hub Development | n/a | n/a | Planned | To be confirmed [Note 12] | Planned | To be confirmed [Note 12] | Maimie Thompson | maimie.thompson@nhs.net
Health | Redevelopment of Royal Edinburgh Hospital Campus - Phase 1 | Provision of 185 bed facility for adult mental health and IPCU patients. | Hospital (New Build) | NHS LOTHIAN | 49,400,000 (revenue funded element: 38,400,000) | Revenue Funded | Hub | In Construction | n/a | n/a | Completed | 21/01/2015 | Planned | 06/12/2016 | Andrew Milne | capital.planning@nhslothian.scot.nhs.uk
Health | Redevelopment of Royal Edinburgh Hospital Campus Phase 2 | This scheme will provide fit-for-purpose accommodation. | Other | NHS LOTHIAN | 98,000,000 - 168,000,000 | Revenue funded | Hub | In hub Development | n/a | n/a | Planned | 2018-03-01 | Planned | 2020-03-01 | Andrew Milne | capital.planning@nhslothian.scot.nhs.uk
Health | Gorbals Health Centre | Provision of a new build development to accommodate 5 GP practices, community health services, including podiatry, physiotherapy, children's services, speech therapy, adult mental health services, community dental and General Dental Practice. | Health Centre | NHS GREATER GLASGOW AND CLYDE | 14,400,000 - 14,900,000 (revenue funded element: 12,900,000-13,500,000) | Revenue funded | Hub | In hub Development | n/a | n/a | Planned | 09/01/2017 | Planned | 24/05/2018 | John Donnelly | john.donnelly@ggc.scot.nhs.uk
Health | NHS Lothian Partnership Centre Bundle | This will include Blackburn, Firrhill and North West Edinburgh Partnership Centres | Health Centre | NHS LOTHIAN | 34,200,000 (revenue funded element: 28,400,000) | Revenue Funded | Hub | In Construction | n/a | n/a | Completed | 2016-05-02 | Planned | 2017-06-01 | Campbell Kerr | capital.planning@nhslothian.scot.nhs.uk
Health | Stirling Care Village | Joint venture between NHS Forth Valley, Stirling Council, Forth Valley College and Scottish Ambulance Service to meet the needs of the local community incorporating health and social care along with leisure, recreational, commercial and educational facilities. | Community Services | NHS FORTH VALLEY | 36,000,000 - 38,000,000 (revenue funded element: 33,000,000 - 35,000,000) | Revenue funded | Hub | In hub Development | n/a | n/a | Planned | 17/10/2016 | Planned | 16/04/2018 | Graeme Bowden | graeme.bowden@nhs.net
Health | Woodside Health Centre | Provision of a new build development to accommodate 8 GP practices, community health services, including podiatry, physiotherapy, children's services, speech therapy, adult mental health services, community dental and pharmacy. | Health Centre | NHS GREATER GLASGOW AND CLYDE | 15,300,000 - 16,000,000 (revenue funded element: 14,400,000- 15,100,000) | Revenue funded | Hub | In hub Development | n/a | n/a | Planned | 09/01/2017 | Planned | 31/05/2018 | John Donnelly | john.donnelly@ggc.scot.nhs.uk
Health | Inverclyde Continuing Care Beds for Mental Health | Provision of facilities for 30 older peoples continuing care beds and 12 adult continuing care beds. | Hospital (New Build) | NHS GREATER GLASGOW AND CLYDE | 8,800,000 (revenue funded element: 8,400,000) | Revenue Funded | Hub | In Construction | n/a | n/a | Completed | 16/05/2016 | Planned | 28/06/2017 | John Donnelly | john.donnelly@ggc.scot.nhs.uk
Health | Redesign of Services for Skye, Lochalsh & South West Ross | To provide appropriate services to the local communities in an efficient and cost effective way from modern facilities and, wherever possible, as close to the service users home as possible and to facilitate integration between Health and Social Care. | Community Services | NHS HIGHLAND | 15,300,000 (revenue funded element: 15,000,000) | Revenue funded | Hub | Pre-hub Development | n/a | n/a | Planned | 07/01/2019 | Planned | 27/11/2020 | Heather Cameron | heather.cameron2@nhs.net
Health | Redesign of Services for Badenoch and Strathspey | To provide appropriate services to the local communities in an efficient and cost effective way from modern facilities and, wherever possible, as close to service users home as possible and to facilitate integration between Health and Social Care. | Community Services | NHS HIGHLAND | 14,500,000- 16,000,000 (revenue funded element: 13,500,000- 15,000,000) | Revenue funded | Hub | Pre-hub Development | n/a | n/a | Planned | 07/01/2019 | Planned | 27/11/2020 | Heather Cameron | heather.cameron2@nhs.net
Health | Inverurie Health Care Hub & Foresterhill Health Centre | Reprovision of a Health Centre for Inverurie to incorporate; GP Practice, Community Midwifery Unit, Radiology and Community Dental services. Reprovision of the Health Centre on the Foresterhill Health Campus site. | Community Services | NHS GRAMPIAN | 23,700,000 (revenue funded element: 21,700,000) | Revenue funded | Hub | In hub Development | n/a | n/a | Planned | 2016-11-01 | Planned | 16/05/2018 | Enquiries Grampian | grampian@nhs.net
Health | Aberdeen Baird Family Hospital and ANCHOR Centre | New Maternity Hospital and Centre for Cancer services in Aberdeen to reprovide services located on the Foresterhill site. The detail of the services included in the project is currently under consideration. | Hospital (New Build) | NHS GRAMPIAN | 156,000,000-157,000,000 | Capital Funded | Framework | In Preparation | n/a | n/a | Planned | 31/03/2018 | Planned | 31/08/2020 | Enquiries Grampian | grampian@nhs.net
Health | East Lothian Community Hospital | This scheme will provide fit-for-purpose accommodation which will comprise 2 phases (indicatively). Phase 1 is the provision of outpatients services and phase 2 the remainder of the community hospital including 132 inpatient beds | Hospital (New Build) | NHS LOTHIAN | 68,000,000-72,000,000 | Revenue funded | Hub | In hub Development | n/a | n/a | Planned | 01/11/2016 | Planned | 31/12/2019 | Andrew Milne | capital.planning@nhslothian.scot.nhs.uk
Health | Clydebank Health & Care Centre | Provision of a new build development to accommodate 6 GP practices, community health services, including podiatry, physiotherapy, children's services, speech therapy, adult and older peoples mental health services. | Health Centre | NHS GREATER GLASGOW AND CLYDE | 20,400,000 (revenue funded element: 19,000,000) | Revenue funded | Hub | In hub Development | n/a | n/a | Planned | 05/02/2018 | Planned | 28/06/2019 | John Donnelly | john.donnelly@ggc.scot.nhs.uk
Health | Greenock Health & Care Centre | Provision of a new build development to accommodate 5GP practices, community health services, including podiatry, physiotherapy, speech therapy, adult mental health services, Sandyford sexual health, community dental, pharmacy and social work. | Health Centre | NHS GREATER GLASGOW AND CLYDE | 20,600,000 (revenue funded element: 19,000,000) | Revenue funded | Hub | In hub Development | n/a | n/a | Planned | 05/02/2018 | Planned | 28/06/2019 | John Donnelly | john.donnelly@ggc.scot.nhs.uk
Schools | South of the City | Scotland's Schools for the Future Programme project | School | ABERDEEN CITY COUNCIL | 47,400,000 (revenue funded element: 44,500,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 10/06/2016 | Planned | 19/08/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Forfar Academy | Scotland's Schools for the Future Programme project | School | ANGUS COUNCIL | 38,300,000 (revenue funded element 34,700,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 01/09/2014 | Planned | 14/02/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Kirn Primary School | Scotland's Schools for the Future Programme project | School | ARGYLL AND BUTE COUNCIL | 10600000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 13/06/2016 | Planned | 10/10/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Campbeltown Grammar | Scotland's Schools for the Future Programme project | School | ARGYLL AND BUTE COUNCIL | 25,700,000 (revenue funded element: 23,500,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 03/05/2016 | Planned | 22/02/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Oban High School | Scotland's Schools for the Future Programme project | School | ARGYLL AND BUTE COUNCIL | 36,000,000 (revenue funded element: 32,700,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 25/04/2016 | Planned | 13/04/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Boroughmuir High School | Scotland's Schools for the Future Programme project | School | CITY OF EDINBURGH COUNCIL | 32000000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Construction | Completed | 11/12/2013 | Completed | 08/10/2014 | Planned | 11/01/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | St John's Primary School | Scotland's Schools for the Future Programme project | School | CITY OF EDINBURGH COUNCIL | 10,100,000 - 10,600,000 | Capital Funded | Conventional Capital Procurement | In Preparation | Completed | 31/08/2015 | Planned | 20/02/2017 | Planned | 19/03/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Craigbank Primary School | Scotland's Schools for the Future Programme project | School | CLACKMANNANSHIRE COUNCIL | 9,800,000 - 11,300,000 | Capital Funded | To be confirmed | In Preparation | Planned | To be confirmed | Planned | To be confirmed | Planned | To be confirmed | Scott Johnston | scott.johnston@gov.scot
Schools | Dalbeattie High School | Scotland's Schools for the Future Programme project | School | DUMFRIES AND GALLOWAY COUNCIL | 25,800,000 (revenue funded element: 24,800,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 07/03/2016 | Planned | 30/10/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Maxwellton High School (previously Crichton Campus) | Scotland's Schools for the Future Programme project | School | DUMFRIES AND GALLOWAY COUNCIL | 12,300,000 - 13,000,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 2016-09-19 | Planned | 2018-06-11 | Scott Johnston | scott.johnston@gov.scot
Schools | Baldragon Academy | Scotland's Schools for the Future Programme project | School | DUNDEE CITY COUNCIL | 29,100,000 (revenue funded element: 28,200,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 29/02/2016 | Planned | 08/01/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | William McIlvanney Campus | Scotland's Schools for the Future Programme project | School | EAST AYRSHIRE COUNCIL | 45,100,000 (revenue funded element: 42,400,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 14/03/2016 | Planned | 29/03/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Barrhead High School | Scotland's Schools for the Future Programme project | School | EAST RENFREWSHIRE COUNCIL | 27,100,000 (revenue funded element: 22,700,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 23/03/2016 | Planned | 14/08/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Carrongrange ASN School | Scotland's Schools for the Future Programme project | School | FALKIRK COUNCIL | 18100000 | Capital Funded | Hub | In Construction | n/a | n/a | Completed | 09/05/2016 | Planned | 16/08/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Clyde Campus | Scotland's Schools for the Future Programme project | School | GLASGOW CITY COUNCIL | 21600000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Construction | Completed | 26/08/2014 | Completed | 25/06/2015 | Planned | 23/10/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Wick High School | Scotland's Schools for the Future Programme project | School | HIGHLAND COUNCIL | 53,800,000 (revenue funded element: 48,500,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 15/07/2014 | Planned | 24/10/2016 | Scott Johnston | scott.johnston@gov.scot
Schools | St Patrick's Primary School | Scotland's Schools for the Future Programme project | School | INVERCLYDE COUNCIL | 7000000 | Capital Funded | Hub | In Construction | n/a | n/a | Completed | 10/08/2015 | Planned | 28/10/2016 | Scott Johnston | scott.johnston@gov.scot
Schools | Newbattle High School | Scotland's Schools for the Future Programme project | School | MIDLOTHIAN COUNCIL | 35,900,000 (revenue funded element: 33,800,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 12/02/2016 | Planned | 30/03/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Milne's Primary School | Scotland's Schools for the Future Programme project | School | MORAY COUNCIL | 2,000,000 - 2,100,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Preparation | Completed | 02/05/2016 | Planned | 16/01/2017 | Planned | 14/08/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Elgin High School | Scotland's Schools for the Future Programme project | School | MORAY COUNCIL | 29,500,000 (revenue funded element: 27,700,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 09/03/2016 | Planned | 23/10/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Garnock Academy | Scotland's Schools for the Future Programme project | School | NORTH AYRSHIRE COUNCIL | 42200000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 16/02/2015 | Planned | 05/01/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Largs Academy | Scotland's Schools for the Future Programme project | School | NORTH AYRSHIRE COUNCIL | 51,900,000 (revenue funded element 44,300,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 30/05/2016 | Planned | 12/03/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Evie Primary School | Scotland's Schools for the Future Programme project | School | ORKNEY ISLANDS COUNCIL | 2900000 | Capital Funded | Conventional Capital Procurement | In Construction | Completed | 01/09/2014 | Completed | 23/03/2015 | Planned | 31/10/2016 | Scott Johnston | scott.johnston@gov.scot
Schools | Kinross Primary School | Scotland's Schools for the Future Programme project | School | PERTH AND KINROSS COUNCIL | 10,200,000 - 10,800,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Hub | In hub Development | n/a | n/a | Planned | 10/10/2016 | Planned | 11/12/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Kersland/Clippens School | Scotland's Schools for the Future Programme project | School | RENFREWSHIRE COUNCIL | 17700000 | Capital Funded | Framework | In Construction | n/a | n/a | Completed | 03/11/2014 | Planned | 15/08/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Duns Primary School | Scotland's Schools for the Future Programme project | School | SCOTTISH BORDERS COUNCIL | 9300000 | Capital Funded | Hub | In Construction | n/a | n/a | Completed | 24/08/2015 | Planned | 06/03/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Kelso High School | Scotland's Schools for the Future Programme project | School | SCOTTISH BORDERS COUNCIL | 24,600,000 (revenue funded element: 21,500,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 14/03/2016 | Planned | 09/01/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Anderson High School | Scotland's Schools for the Future Programme project | School | SHETLAND ISLANDS COUNCIL | 64,400,000 (revenue funded element: 40,600,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 26/06/2015 | Planned | 07/09/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Ayr Academy | Scotland's Schools for the Future Programme project | School | SOUTH AYRSHIRE COUNCIL | 25,100,000 (revenue funded element: 24,400,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 30/01/2016 | Planned | 17/08/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Marr College | Scotland's Schools for the Future Programme project | School | SOUTH AYRSHIRE COUNCIL | 37000000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 29/06/2015 | Planned | 06/01/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Halfmerke Primary School and West Mains School | Scotland's Schools for the Future Programme project | School | SOUTH LANARKSHIRE COUNCIL | 11500000 | Capital Funded | Framework | In Construction | n/a | n/a | Completed | 31/03/2015 | Planned | 09/01/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | St Ninian's Primary School | Scotland's Schools for the Future Programme project | School | STIRLING COUNCIL | 8300000 | Capital Funded | Hub | In Construction | n/a | n/a | Completed | 05/10/2015 | Planned | 06/10/2016 | Scott Johnston | scott.johnston@gov.scot
Schools | Our Lady & St Patrick's High School | Scotland's Schools for the Future Programme project | School | WEST DUNBARTONSHIRE COUNCIL | 26,700,000 (revenue funded element: 25,900,000) | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 11/04/2016 | Planned | 23/10/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | West Calder High School | Scotland's Schools for the Future Programme project | School | WEST LOTHIAN COUNCIL | 38900000 | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 19/09/2016 | Planned | 01/06/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Paradykes Primary School | Scotland's Schools for the Future Programme project | School | MIDLOTHIAN COUNCIL | 15600000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Construction | Completed | 06/10/2015 | Completed | 06/06/2016 | Planned | 16/08/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Roslin Primary School | Scotland's Schools for the Future Programme project | School | MIDLOTHIAN COUNCIL | 7200000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Construction | Completed | 06/10/2015 | Completed | 13/06/2016 | Planned | 31/03/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Broomlands Primary School | Scotland's Schools for the Future Programme project | School | SCOTTISH BORDERS COUNCIL | 5,400,000 - 5,700,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | Advertised to Market | Completed | 13/07/2015 | Planned | 2016-10-10 | Planned | 2017-12-16 | Scott Johnston | scott.johnston@gov.scot
Schools | Langlee Primary School | Scotland's Schools for the Future Programme project | School | SCOTTISH BORDERS COUNCIL | 10900000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Construction | Completed | 13/07/2015 | Completed | 09/05/2016 | Planned | 15/06/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Toronto Primary School | Scotland's Schools for the Future Programme project | School | WEST LOTHIAN COUNCIL | 2500000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Construction | Completed | 10/08/2015 | Completed | 04/12/2015 | Planned | 17/10/2016 | Scott Johnston | scott.johnston@gov.scot
Schools | Dunoon Primary School | Scotland's Schools for the Future Programme project | School | ARGYLL AND BUTE COUNCIL | 7,200,000 - 7,600,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Hub | In hub Development | n/a | n/a | Planned | 03/04/2017 | Planned | 04/04/2019 | Scott Johnston | scott.johnston@gov.scot
Schools | Tain Campus | Scotland's Schools for the Future Programme project | School | HIGHLAND COUNCIL | 29,700,000 -31,300,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Preparation | Planned | 09/01/2017 | Planned | 22/09/2017 | Planned | 13/08/2019 | Scott Johnston | scott.johnston@gov.scot
Schools | Millbank Primary School | Scotland's Schools for the Future Programme project | School | MORAY COUNCIL | 4900000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Framework | In Construction | n/a | n/a | Completed | 06/07/2015 | Planned | 31/03/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Seafield Primary School | Scotland's Schools for the Future Programme project | School | MORAY COUNCIL | 6700000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Framework | In Construction | n/a | n/a | Completed | 06/07/2015 | Planned | 31/03/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Bellsbrae Primary School | Scotland's Schools for the Future Programme project | School | SHETLAND ISLANDS COUNCIL | 700000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Construction | Completed | 25/01/2016 | Completed | 29/03/2016 | Planned | 29/09/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Sound Primary School | Scotland's Schools for the Future Programme project | School | SHETLAND ISLANDS COUNCIL | 700000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Construction | Completed | 27/01/2015 | Completed | 30/03/2015 | Planned | 01/12/2016 | Scott Johnston | scott.johnston@gov.scot
Schools | The Waid | Scotland's Schools for the Future Programme project | School | FIFE COUNCIL | 24000000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 09/11/2015 | Planned | 31/03/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | TBC (New Secondary School) | Scotland's Schools for the Future Programme project | School | PERTH AND KINROSS COUNCIL | 28,700,000 - 30,200,000 | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In hub Development | n/a | n/a | Planned | 15/08/2017 | Planned | 13/08/2019 | Scott Johnston | scott.johnston@gov.scot
Schools | Balloch Campus (Inc. St Kessogs, Jamestown, Haldane) | Scotland's Schools for the Future Programme project | School | WEST DUNBARTONSHIRE COUNCIL | 16500000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Construction | Completed | 04/01/2016 | Completed | 22/07/2016 | Planned | 23/10/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | St Josephs College | Scotland's Schools for the Future Programme project | School | DUMFRIES AND GALLOWAY COUNCIL | 12,200,000 - 12,800,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Hub | In Construction | n/a | n/a | Completed | 15/08/2016 | Planned | 12/02/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Bellsbank Primary School | Scotland's Schools for the Future Programme project | School | EAST AYRSHIRE COUNCIL | 3,200,000 - 3,400,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | Advertised to Market | Completed | 11/09/2015 | Planned | 02/03/2017 | Planned | 29/03/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Muirkirk Primary School | Scotland's Schools for the Future Programme project | School | EAST AYRSHIRE COUNCIL | 5900000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Construction | Completed | 14/09/2015 | Completed | 25/07/2016 | Planned | 16/08/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | St Sophia's Primary School | Scotland's Schools for the Future Programme project | School | EAST AYRSHIRE COUNCIL | 1,700,000 - 1,800,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Preparation | Completed | 01/12/2015 | Planned | 01/12/2016 | Planned | 08/01/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Stoneywood Primary School | Scotland's Schools for the Future Programme project | School | ABERDEEN CITY COUNCIL | 5,000,000 - 5,200,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Preparation | Completed | 01/06/2015 | Planned | 2016-10-31 | Planned | 08/01/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Applegrove Primary School | Scotland's Schools for the Future Programme project | School | MORAY COUNCIL | 4800000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Framework | In Construction | n/a | n/a | Completed | 06/07/2015 | Planned | 31/03/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | St Gerardine Primary School | Scotland's Schools for the Future Programme project | School | MORAY COUNCIL | 5000000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Framework | In Construction | n/a | n/a | Completed | 06/07/2015 | Planned | 31/03/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Dundee Joint Campus | Scotland's Schools for the Future Programme project | School | DUNDEE CITY COUNCIL | 18,900,000 - 19,800,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Framework | In Preparation | n/a | n/a | Planned | 01/04/2017 | Planned | 20/08/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Crookfur Primary School | Scotland's Schools for the Future Programme project | School | EAST RENFREWSHIRE COUNCIL | 7800000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Construction | Completed | 21/09/2015 | Completed | 22/03/2016 | Planned | 14/08/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Tulloch Primary School | Scotland's Schools for the Future Programme project | School | PERTH AND KINROSS COUNCIL | 8,600,000 - 9,100,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Hub | In hub Development | n/a | n/a | Planned | 01/12/2016 | Planned | 07/02/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Knockroon Learning and Enterprise Campus (previously 3 into 1 - Greenmill, Barshare, Hillside part of 2-18 Enterprise Campus) | Scotland's Schools for the Future Programme project | School | EAST AYRSHIRE COUNCIL | 17,400,000 - 18,300,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Conventional Capital Procurement | In Preparation | Planned | 01/12/2016 | Planned | 03/07/2017 | Planned | 14/08/2019 | Scott Johnston | scott.johnston@gov.scot
Schools | Inverurie | Scotland's Schools for the Future Programme project | School | ABERDEENSHIRE COUNCIL | 36,300,000 - 38,200,000 | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | Pre-hub Development | n/a | n/a | Planned | 01/01/2018 | Planned | 30/03/2020 | Scott Johnston | scott.johnston@gov.scot
Schools | Hayshead | Scotland's Schools for the Future Programme project | School | ANGUS COUNCIL | 11,400,000 - 11,900,000 | D&B school supported by revenue funded NPD/hub programme as part of a group | Hub | Pre-hub Development | n/a | n/a | Planned | 01/05/2017 | Planned | 14/08/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Ladyloan | Scotland's Schools for the Future Programme project | School | ANGUS COUNCIL | 8,500,000 - 8,900,000 | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | Pre-hub Development | n/a | n/a | Planned | 01/05/2017 | Planned | 14/08/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Muirfield | Scotland's Schools for the Future Programme project | School | ANGUS COUNCIL | 8,600,000 - 9,000,000 | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | Pre-hub Development | n/a | n/a | Planned | 01/05/2017 | Planned | 22/02/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Tullibody South | Scotland's Schools for the Future Programme project | School | CLACKMANNANSHIRE COUNCIL | 10,400,000 - 10,900,000 | Capital Funded | Hub | Pre-hub Development | n/a | n/a | Planned | 13/09/2017 | Planned | 26/02/2019 | Scott Johnston | scott.johnston@gov.scot
Schools | St Agatha's | Scotland's Schools for the Future Programme project | School | EAST DUNBARTONSHIRE COUNCIL | 8600000 | Capital Funded | Hub | In Construction | n/a | n/a | Completed | 06/06/2016 | Planned | 18/04/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Wallyford | Scotland's Schools for the Future Programme project | School | EAST LOTHIAN COUNCIL | 8,900,000 - 9,300,000 | Capital Funded | Hub | Pre-hub Development | n/a | n/a | Planned | 01/08/2017 | Planned | 01/12/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Queensferry | Scotland's Schools for the Future Programme project | School | CITY OF EDINBURGH COUNCIL | 29,000,000 - 30,500,000 | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | Pre-hub Development | n/a | n/a | Planned | 2018-01-05 | Planned | 2020-01-07 | Scott Johnston | scott.johnston@gov.scot
Schools | Blairdardie | Scotland's Schools for the Future Programme project | School | GLASGOW CITY COUNCIL | 9,900,000 - 10,400,000 | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In hub Development | n/a | n/a | Planned | 10/07/2017 | Planned | 20/08/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Carntyne | Scotland's Schools for the Future Programme project | School | GLASGOW CITY COUNCIL | 5,600,000 - 5,900,000 | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | In hub Development | n/a | n/a | Planned | 10/07/2017 | Planned | 20/08/2018 | Scott Johnston | scott.johnston@gov.scot
Schools | Alness | Scotland's Schools for the Future Programme project | School | HIGHLAND COUNCIL | 21,200,000 -22,300,000 | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | Pre-hub Development | n/a | n/a | Planned | 01/04/2018 | Planned | 28/02/2020 | Scott Johnston | scott.johnston@gov.scot
Schools | Kilmalcolm | Scotland's Schools for the Future Programme project | School | INVERCLYDE COUNCIL | 4300000 | Capital Funded | Hub | In Construction | n/a | n/a | Completed | 19/10/2015 | Planned | 28/10/2016 | Scott Johnston | scott.johnston@gov.scot
Schools | Lossiemouth High School | Scotland's Schools for the Future Programme project | School | MORAY COUNCIL | 26,000,000 - 27,400,000 | DBFM school supported by revenue funded NPD/hub programme as part of a group | Hub | Pre-hub Development | n/a | n/a | Planned | 01/03/2018 | Planned | 01/03/2020 | Scott Johnston | scott.johnston@gov.scot
Schools | Cumbernauld (Previously Cumbernauld High & Abronhill High) | Scotland's Schools for the Future Programme project | School | NORTH LANARKSHIRE COUNCIL | 31,800,000 - 33,400,000 | Revenue funded | Hub | In hub Development | n/a | n/a | Planned | 2017-07-10 | Planned | 2019-08-15 | Scott Johnston | scott.johnston@gov.scot
Schools | St Fergus | Scotland's Schools for the Future Programme project | School | RENFREWSHIRE COUNCIL | 5300000 | Capital Funded | Framework | In Construction | n/a | n/a | Completed | 14/04/2016 | Planned | 18/04/2017 | Scott Johnston | scott.johnston@gov.scot
Schools | Queen Margaret | Scotland's Schools for the Future Programme project | School | SOUTH AYRSHIRE COUNCIL | 24,700,000 - 26,000,000 | Revenue funded | Hub | Pre-hub Development | n/a | n/a | Planned | 01/10/2017 | Planned | 01/06/2019 | Scott Johnston | scott.johnston@gov.scot
Schools | Burnside | Scotland's Schools for the Future Programme project | School | SOUTH LANARKSHIRE COUNCIL | 7700000 | Capital Funded | Framework | In Construction | n/a | n/a | Completed | 09/11/2015 | Planned | 10/03/2017 | Scott Johnston | scott.johnston@gov.scot
Further Education / Higher Education | Ayrshire College Kilmarnock Campus | Campus relocation | FE College | AYRSHIRE COLLEGE | 53,600,000 (revenue funded element: 48,500,000) | Revenue Funded | NPD (Non Profit Distributing) | In Construction | Completed | 28/03/2012 | Completed | 25/06/2014 | Planned | 2016-10-24 | Nicholas Dixon | ndixon@sfc.ac.uk
Further Education / Higher Education | City of Glasgow College | To create a new estate for the City of Glasgow College; formed in 2010 through the merger of three former city centre colleges. | FE College | CITY OF GLASGOW COLLEGE | 228,600,000 (revenue funded element: 193,000,000) | Revenue Funded | NPD (Non Profit Distributing) | Operational [Note 13] | Completed | 02/12/2011 | Completed | 30/08/2013 | Planned | 14/08/2017 [Note 13] | Nicholas Dixon | ndixon@sfc.ac.uk
Further Education / Higher Education | Fife College (Dunfermline Campus) | New build in Dunfermline. | FE College | FIFE COLLEGE | 86,000,000 (revenue funded element: 70,000,000) | Revenue funded | NPD (Non Profit Distributing) | OBC Approved | Planned | 01/03/2017 | Planned | 01/07/2018 | Planned | 01/08/2020 | Nicholas Dixon | ndixon@sfc.ac.uk
Further Education / Higher Education | Forth Valley College (Falkirk Campus) | New build to replace the existing FVC Falkirk campus, which is no longer fit-for purpose. | FE College | FORTH VALLEY COLLEGE | 83000000 | Capital Funded | Conventional Capital Procurement | OBC Approved | Planned | 01/11/2016 | Planned | 01/09/2017 | Planned | 01/10/2019 | Nicholas Dixon | ndixon@sfc.ac.uk
Culture | V&A Dundee | Construction of new building on Dundee Waterfront. The V&A Dundee will be an international centre of 21st century design. | Museum/Art Gallery | DUNDEE CITY COUNCIL | 80100000 | Capital Funded | Conventional Capital Procurement | In Construction | Completed | 16/08/2013 | Completed | 05/03/2015 | Planned | 30/06/2018 | Duncan MacKay | duncan.mackay@gov.scot
Justice | HMP Highland | By replacing an old and unfit prison, HMP Highland will provide a fit-for-purpose community facing prison, which supports the Government's objective of reducing the risk of prisoners reoffending on release from custody. | Prison | SCOTTISH PRISON SERVICE | 66000000 | Capital Funded | Conventional Capital Procurement | In Preparation | Planned | 31/03/2017 | Planned | 15/10/2018 | Planned | 03/08/2020 | Projects Scottish Prison Service | gaolinfo@sps.pnn.gov.uk
Justice | HMP Glasgow | By replacing an old and unfit prison, HMP Glasgow will provide a fit-for-purpose community facing prison, which supports the Government's objective of reducing the risk of prisoners reoffending on release from custody. SPS will award a contract for the design and construction of HMP Glasgow either on the site of HMP Barlinnie or a site to be acquired by SPS. | Prison | SCOTTISH PRISON SERVICE | 170000000 | Capital Funded | Conventional Capital Procurement | In Preparation | Planned | 01/06/2018 | Planned | 01/04/2020 | Planned | 02/10/2023 | Projects Scottish Prison Service | gaolinfo@sps.pnn.gov.uk
Justice | National Facility for Women Offenders | Construction of a new national facility which forms part of the Scottish Government's vision for the management of women in custody. | Prison | SCOTTISH PRISON SERVICE | 45000000 | Capital Funded | Conventional Capital Procurement | In Preparation | Planned | 2016-11-01 | Planned | 01/10/2018 | Planned | 01/10/2020 | Projects Scottish Prison Service | gaolinfo@sps.pnn.gov.uk
Justice | HMP Greenock (R) | By replacing an old and unfit prison, HMP Greenock (R) will provide a fit-for-purpose prison, which supports the Government's objective of reducing the risk of prisoners reoffending on release from custody. | Prison | SCOTTISH PRISON SERVICE | 75000000 | Capital Funded | Conventional Capital Procurement | In Preparation | Planned | 16/01/2017 | Planned | 01/10/2018 | Planned | 29/01/2021 | Projects Scottish Prison Service | gaolinfo@sps.pnn.gov.uk
Justice | Inverness Justice Centre | Provision of first Justice Centre in Scotland | Court | SCOTTISH COURT SERVICE | 23500000 | Capital Funded | Framework | OBC Approved | n/a | n/a | Planned | 2017-05-01 | Planned | 2019-04-01 | David Currie | dcurrie@scotcourts.gov.uk
Notes relating to the updated IIP Project Pipeline 1. The ‘IIP - Project Pipeline’ relates to those projects with a capital value of £20 million or more where the Scottish Government has a lead role in procurement or funding. It also includes school projects which are being delivered through the Scotland’s Schools for the Future Programme and those health projects being taken forward through the Scotland-wide 'hub' initiative which form part of the Scottish Government's current revenue funded £3.5 billion NPD/hub investment programme. The majority of the information relates to that as of 31 August 2016. However if there has been a significant change in the status of a project between this date and 30 September 2016, then information relating to that project has been updated as is relevant. 2. The following projects within the previously published pipeline in March 2016 are now operational and are subsequently no longer included: • NHS Ayrshire and Arran - Acute Mental Health & North Ayrshire Community Hospital; • NHS Greater Glasgow and Clyde - Maryhill Health Centre; • NHS Greater Glasgow and Clyde - Eastwood Health & Care Centre; • NHS Lanarkshire Primary Care Health Centres; • James Gillespie's High School, City of Edinburgh Council; • North Uist Primary School, Comhairle nan Eilean Siar / Western Isles Council; • Harris Academy, Dundee City Council; • Levenmouth High School, Fife Council; • Glendale Primary School, Glasgow City Council; • Inverness Royal Academy, Highland Council; • Greenfaulds High School, North Lanarkshire Council; • Lenzie / Lenzie Moss Primary School, East Dunbartonshire Council. 3. The Total Capital Investment estimates include the construction contract costs and any associated capital funded costs such as land acquisition and enabling works (e.g. demolition and utilities diversions). For revenue funded projects which have associated capital funded costs, the revenue funded contract values representing the value of the Scottish Government funded construction activity associated with the project have also been included in brackets within the Total Capital Investment costs. These have been included in order to provide transparency around delivery of the current revenue funded £3.5 billion NPD/hub investment programme. For all projects in development through Scotland’s Schools for the Future programme, the Total Capital Investment relates to the estimated project cost of each school based on the metrics used for the Programme (these figures do not include additional related capital elements incurred by local authorities for additional works which are out with the scope of the programme). For those school projects which are in construction, the total actual costs are provided where finalised, (these include additional related capital elements incurred by local authorities for additional works which are out with the scope of the programme). 4. Estimated costs for individual projects will change until the project has reached completion. Cost estimates for individual projects may rise or fall for a number of reasons, including: changes to the scope of the project; incurring unanticipated or additional costs for preparatory works; costs arising from unavoidable delay to projects; and increases in input costs and construction prices. 5. An estimate for inflation over the delivery period is included. Exceptions include those projects where it is too early to provide an estimate, those projects where costs are contractually fixed and those projects where costs relate to a specific year (e.g. 2014 prices). How inflation is managed will vary between contracts and will depend on how far the project has progressed in its delivery. 6. All figures rounded to the nearest £100,000. 7. For revenue funded NPD/hub projects which have reached financial close and are in construction, links have been provided to the schedule of estimated unitary payment charges (where finalised for publication) which will be paid over the lifetime of the contracts. Note that DBFM is an acronym for Design, Build, Finance & Maintain and that D&B is an acronym for Design & Build. 8. Those projects which do not yet have an Outline Business Case approved (or equivalent) have been marked as ‘In Preparation’ with the exception of those projects being procured by way of the hub initiative. Those projects being procured by way of the hub initiative which are not yet in construction have been marked as the following: • 'Pre hub Development' (a new project request has not yet been received by hubco from procuring local authority); or • ‘In hub Development’ (a new project request has been submitted to hubco from procuring local authority and project is continuing through hub development process). Estimated delivery dates for these projects are provided where known. 9. Project milestones relate to the principal construction contract for each of the projects included. Contracting and procurement processes vary for those projects being delivered by way of Network Rail, the hub initiative or Framework Agreements. Consequently these projects have ‘n/a’ (not applicable) for ‘Project Advertised to Market’. Estimated delivery dates for projects are provided where known. Timescale estimates for individual projects may be lengthened or shortened for a number of reasons, including: changes to the scope of the projects; unanticipated or unavoidable delays to construction; unanticipated or unavoidable delays in the procurement process; and the impact of considerations around affordability for the procuring authority. 10. For further information on any project within this pipeline, please contact the relevant area at the e-mail address provided in ‘Contact For Public Enquiries’. 11. A90/A96 Haudagain Junction Improvement - estimated costs have not been included as statutory procedures are not completed. Draft Orders for the scheme were published in June 2015 with Transport Scotland currently trying to resolve objections received. A Public Local Inquiry may be required to resolve outstanding objections. 12. Redesign of Mental Health Facilities Argyll & Bute – the project is currently on hold as there has been a review of both clinical and support services which have had a significant impact upon requirements for any potential new build. The requirements are much reduced from the previous proposal. The next step will be a re-evaluation of requirements based on the service reviews followed by an option appraisal. 13. City of Glasgow College - As of August 2016, the project is operational following the City Centre Campus opening (Riverside Campus having been in operation since August 2015). There are still phased external works remaining to be completed for both campuses and these will be fully completed by 2017 (Riverside, October 2016 and City Centre, August 2017).