## QWs
INDEPENDENT CONSENTING REVIEW – RECOMMENDATIONS PROGRESS TABLE
Quick Wins |  | Actions | Progress | Lead | Timescale | Comments
QW1 | Strengthen the pre-application process | Inform developers of the process and ensure the SSPO Industry Protocol for Pre-Application is readily available on the Scottish Aquaculture website. | Complete | SSPO, LAs | n/a | n/a
|  | Review SSPO Protocol, update for shellfish and include clear guidance on how to initiate discussions with relevant authorities, regulators and statutory consultees. | Complete | ASSG | n/a | ASSG has advised that the pre-application process will be contained within its forthcoming Shellfish Code of Good Practice, noting a limited need for separate good practice guidance in respect of shellfish pre-app due to the relatively small scale of most developments. In addition, cost burdens on shellfish farmers are felt to reduce the desire for wider non-statutory application of the pre-app process to shellfish farming. Including advice in the Code and the identification of a need to monitor cost burdens should pre-app requirements increase are the outcomes from this action point
|  | Ensure the Protocol includes an up-to-date pro-forma with an information checklist to be provided confidentially to statutory consultees allowing identification of immediate showstoppers. | Complete | SG | n/a | Discussed at the 9 February 2018 workshop with the Heads of Local Authority Planning Departments and industry. Accepted that much work has gone into pre-app from both industry and local authorities that means no further immediate actions are required. Observed that future training needs of local authority planners may need to take into account the need to continue and build on the existing good practice that was spoken about at the workshop. To note: some pre-application issues such as EIA templates and Working Arrangements were identified as requiring further attention but there are seperate quick wins for these issues.
|  | Support a tiered pre-application discussion process so that advice can be updated when relevant information becomes available e.g. benthic surveys. | Complete | SG | n/a
|  | Explore potential scope for a pre-application screening checklist which leads to a 'likely to be consentable' or 'not likely to be consentable' first step | Complete | SG | n/a
QW2 | Introduce consistent format for co-ordinates, site name and summary information | Standardise the required site summary information across all applications. | Complete | CE, SEPA, LAs, SG | n/a | Regulatory bodies have a rationale for the use of a particular coordinates system (this will depend as to whether they work predominantly in the marine or terrestrial environment) and standardising this is therefore impracticable. As a compromise The Crown Estate Scotland developed a process by which a schedule of coordinates in different formats is issued following the application of a Lease Option Agreement (to secure the seabed). This is of most use to the shellfish industry.
|  | Standardise format of co-ordinates across all applications. Seek agreement from regulators as to the appropriate format. | Complete | CE, SEPA, LAs, SG | n/a
|  | Promote, assist and support the industry in improving the quality of application submissions providing requisite attention to detail of all specific requirements. | TBC | CWG | TBC | QW2 is complete but further actions on this specific action point are to be considered by the CWG.
QW3 | Update of Working Arrangements document | Reflect current arrangements and agree most efficient engagement with consultees. Other goals: • Clearly identify responsibilities across authorities/regulators and statutory consultees. • Ensure it is available on the Scottish Aquaculture portal. • Update via frequent review cycles to ensure any changes are accurately reflected e.g. every three years. | In progress | SG | Spring 2018 | Working Group established to take work forward. Next iteration of the document with the statutory consultees to the planning process for comments. Discussed at the 9 February 2018 workshop between Heads of LA planning and industry and agreed that Marine Scotland will set up a workshop to discuss this and EIA templates (QW7) given the close correlation between the two matters.
QW4 | Integrate wellboat Marine Licence into the CAR Licence | Integrate wellboat Marine Licence into the CAR Licence. It is understood that this would: -require one additional sentence to be added to the CAR Licence. -cover all wellboat discharges. -Be supported by SEPA and the finfish industry. | In progress | SG, SEPA | 2018 | Further consideration determined that the process was more detailed than the report had suggested. Changes require public consultation before secondary legislation can be finalised and this will then be subject to Parliamentary scrutiny. In addition, a 6 month delay is also required between the Order being laid and coming into force to allow time for SEPA to review and vary all licences. There remains agreement to make changes. Required legislative changes are under consideration.
QW5 | Update Scottish Aquaculture portal | Ensure it includes: • easily accessible links to relevant licence/consent applications. • relevant regulation, guidance and advice. • up-to-date contacts for key personnel. • link to SEPA's webpage for CAR applications | Complete | SG | n/a | Was agreed that the most appropriate location for relevant regulation, guidance and advice to be Marine Scotland’s webpages. Amendments have been taken forward to these pages.
|  | Include detailed information on all planning consent (i.e. on the map) and allow direct access to monitoring and survey reports where possible. | No plans to progress | SG | n/a | There is currently a rolling care and maintenance programme for Scotland’s Aquaculture. Adding planning information to Scotland’s Aquaculture has been considered in the past but will require significant resource and funding and this has not been identified or prioritised.
QW6 | Support provision of electronic application forms | • Ensure forms can be downloaded and competed electronically (e.g. word) rather than hand written for Marine Licences and Planning Permission application forms. • Review formatting of Marine Licence (which currently has various fonts and font sizes) • Within the Marine Licence form include a check box stating whether the site is within a Harbour Authority area or not, and if so, which Harbour Authority. | Complete with some additional plans being considered | SG, LAs | n/a | In addition to the recommendation that was made, a further programme of work is being undertaken by SG's edevelopment.scot service. Marine Scotland has had discussions about the possibility of enabling aquaculture companies to use ePlanning for fish farm development applications. The practicalities and financial considerations are now under consideration. The Chief Planner indicated at the 9 February 2018 workshop with Heads of LA planning and industry that this will examined in the near future but is not an immediate priority. Members of the CWG have raised their concerns over the 5MB file size limit for ePlanning. Marine Scotland have raised this issue with eDevelopment colleagues. This is an issue common to all developers. Advice is to split the documents into sections and reduce quality of images as local authorities mindful of need to make documents publicly available on websites. In addition, there is an issue of accessibility for members of the public, particularly in rural areas with narrow bandwidths.
QW7 | Update EIA template | - Structure/roles are addressed and that information requirements and format can be optimised. - Fit for purpose and supports streamlined, site specific reporting. - Provide guidance on a Screening/Scoping report. - Provide links to relevant guidance for completing EIA topics, including landscape and visual and commercial fisheries. - MSS to provide clear guidance on information requirements. | In progress | SG, LAs | Jan. 2018 | Versions of the relevant documents have been circulated to stakeholders for comment. Discussed at the 9 February 2018 workshop between Heads of LA planning and industry and agreed that Marine Scotland will set up a workshop to discuss this and the Working Arrangements (QW3) document given the close correlation between the two matters.
QW8 | Hold a Landscape and Visual Impact Assessment workshop | Hold a Landscape and Visual Impact Assessment workshop between SNH, LAs and industry to: - Provide practical advice on what is required within LVIA. - Discuss how viewpoints are chosen. - Share knowledge on expected standards of assessments. - agree with industry how to implement the landscape/seascape policy of SNH and LAs. | Complete | SNH | n/a | Held 01/03/17

## ACOs
INDEPENDENT CONSENTING REVIEW – RECOMMENDATIONS PROGRESS TABLE
Alternative Consenting Options |  | Actions | Progress | Responsibility | Timescale | Comments
AC01 | Consolidate Marine Licencing (for Moorings and Equipment) into Planning Permission | 1a. Review the moorings and equipment Marine Licence form for finfish and shellfish aquaculture, determine any sections that are not covered by planning permission and amalgamate them into the planning permission application form. This will allow Marine Licences to be awarded by default when Planning Permission has been consented. This action amalgamates the application processes, but does not remove the Marine Licence altogether. [It is recommended that this action be prioritised]. | In progress | SG | SUGGESTED MID-LATE 2018 (for any legislation to come into force) *Subject to Parliamentary approval | MS-LOT are currently considering a number of amendments to the Marine Licencing system that will simplify the process for applicants. Meeting to discuss issue held within the Scottish Government. Details are still being considered – while appears possible to amend for new developments, modifications likely to be resource intensive and complex). Capacity Working Group still consider there is value in progressing this for new developments even if this means 2 systems are in operation. Any changes will require public consultation and parliamentary scrutiny. To be considered further.
|  | 1b. Use application form as updated in 1.a to develop one specific form for shellfish and one for finfish. This will reduce the burden, eliminate confusion and assist the shellfish industry in completing application forms. | In progress | SG
|  | 1c. Update the consultation status of MCA and NLB to statutory in the planning permission process. [It is recommended that this action be prioritised]. | In progress | SG
|  | 1d. Consider aligning the (currently 6-year) review cycle, that updates UK Hydrographic Office, into a condition of planning, subject to consultation with NLB and agreement with LAs. | In progress | SG
|  | 1e. Remove aquaculture from Marine Licencing requirements via legislative change. This should be considered after reviewing experience with the above arrangements (1a-1.d) and would fully integrate the objective of Marine Licensing (ensuring navigational safety) within Planning Permission. | In progress | SG
AC02 | Aquaculture Act: Remove aquaculture from the Town and Country Planning Act and introduce a specific Aquaculture Act | 2a. Review the definition of fish farming as a 'development' within the 1997 Act (as set out in Circular 1/2007 Planning Controls for Marine Fish Farming) to allow aquaculture related equipment to be partly or wholly removed for normal husbandry operations without relinquishing planning permission (e.g. specify its change to a 'use' as it is for other terrestrial business activities such as caravan parks). [It is recommended that this action be prioritised]. | In progress | SG | SUGGESTED MID-LATE 2018 (for changes to be made to definition of development if undertaken through Planning Bill) Subject to Parliamentary approval | There is some concern that the legislation is ambiguous with regard to normal aquaculture operations. Permitted Development Rights were introduced in 2012 to ensure routine operations (with limited environmental impact) can be undertaken. These have been reviewed and a consultation was published on 5 May 2017 to further improve certainty for industry in relation to undertaking routine operations. While noting that guidance cannot make law, we consider that changes to Scottish Government guidance could improve matters in the short term and will be taking forward amendments to the Working Arrangements document and developing a new Planning Circular and on-line guidance. Marine Scotland have communicated to colleagues from the Planning Directorate that a change to the definition of development is a priority for industry and policy. Ministers signalled in the Programme for Government that a Planning Bill would be brought forward early in the Parliamentary Session. A consultation on the key components of the legislation closed on 4 April 2017 and analysis is being undertaken. A decision on scope will be made in due course following that analysis. Marine Scotland developed a benefits and issues paper of a single consent (i.e. an Aquaculture Act) for the Capacity Working Group. All members concluded that improvements to the planning system should be made in the first instance. Industry members of the Capacity Working Group have noted their desire for further discussion on an alternative consenting system outwith the terrestrial planning system.
|  | 2b. Reconsider the potential to codify existing legislation into an Aquaculture Act when the consenting process is considered to be efficient/optimal e.g. via a review in 5 years. | n/a at present | SG | Once 2a is complete
AC03 | Align the CAR and Planning Permission consents (finfish aquaculture only) | 3a. Agree working procedures and arrangements between Local Authorities, SEPA and all statutory consultees to enable the alignment of CAR and Planning Permission consents and therefore a fast-tracked consenting process. [This could be delivered as part of the Working Arrangements document update or as a standalone procedure] 3b. Support facilitation of one HRA and associated Appropriate Assessment by standardising the format for reporting and setting out clear procedure (e.g. within Working Arrangements document) 3c. Implement a pilot period to test appropriateness of aligned consents. Assess outcome of the pilot period to determine if alignment should be made mandatory. | No plans to progress | SEPA, LAs | n/a | The Capacity Working Group consider that progressing this recommendation would add an additional layer of bureaucracy to the consenting system without a corresponding reduction in regulatory burden. This issue is not therefore being considered further at this stage.
AC04 | One-stop shop | 4a. Review efficiencies achieved by Options 1 and 3 (after they have been fully implemented) to assess results and determine whether a one-stop shop option would provide further gains. | No plans to progress | SG, regulators, consenting bodies and statutory consultees | n/a | Marine Scotland developed a benefits and issues paper of a one-stop shop for the Capacity Working Group. The Capacity Working Group consider that progressing this recommendation would add an additional layer of bureaucracy to the consenting system without a corresponding reduction in regulatory burden; doing little to resolve existing duplication or uncertainty. This issue is not therefore being considered further at this stage.
AC05 | Removal of wild fish interactions from Planning Permission | 5a. To support the analysis of risk - ensure monitoring and reporting of sea lice within farmed salmonids is reported at a site level. This will require discussion and agreement between the finfish industry and MSS-FHI on how this is to be implemented, recorded and reported. [This assumes the decision remains within Planning Permission in the short-term] | No plans to progress | SG | n/a
|  | 5b. To address provision of scientific advice - form a joint agency approach (e.g. as part of the National Technical Group, which is currently being formed/under discussion) between MSS-FHI, MSS-FFL, SNH, DSFBs and SEPA to take account of information on sea lice levels, treatments, wild fish monitoring and Natura information to enable provision of site specific advice and evaluation that gives a clear steer as to when an aquaculture proposal should be considered acceptable or not with regard to potential wild fish interactions. This could be based on an assessment of risk in data deficient instances. [This assumes the decision remains within Planning Permission in the short-term] | In progress | SG | Improvement of wild fish advice by Marine Scotland by November 2017 | Marine Scotland have held 3 meetings with local authorities to progress an improvement to advice on impacts on wild fish. Agreed that this will include the use of heat maps to indicate sensitivity of location, up-to-date scientific understanding and any relevant sea lice information.