## Sheet1
RMS Detailed Defect Data extract
Road | Section | Chainage | Defect Reference | Defect Date/Time | Defect Category | Item Category | Item Detail | Comments | Perm Repair Date | Status | Easting | Northing | Inspection Name
A76 | 13206/29 | Chainage: 71m | NSW73-610235-237996922 | 2021-01-29 12:23 | CATEGORY 1 | Carriageways | Pothole (POTH) | CAT 1 1ST TIME PERM POTHOLE | 2021-01-29 17:40 | Completed Defects | 286132 | 602086 | Safety Patrol of NSW A76 Winter Safety Patrol Route on 29 January 2021
A76 | 13206/29 | Chainage: 45m | NSW73-617618-238009322 | 2021-03-02 11:46 | CATEGORY 1 | Carriageways | Pothole (POTH) | CAT 1 1ST TIME PERM POTHOLE | 2021-03-02 11:55 | Completed Defects | 286080 | 602051 | Safety Inspection of NSW A76 Safety Inspection Route on 02 March 2021
A76 | 13206/15 | Chainage: 1882m | NSW73-617618-238009323 | 2021-03-02 11:52 | CATEGORY 1 | Carriageways | Pothole (POTH) | CAT 1 1ST TIME PERM POTHOLE | 2021-03-02 11:55 | Completed Defects | 286084 | 601868 | Safety Inspection of NSW A76 Safety Inspection Route on 02 March 2021
A76 | 13206/15 | Chainage: 15m | NSW92-621123-428 | 2021-03-17 11:08 | CATEGORY 2 | Road Traffic Signs | Dirty Signs (DIRT) | X2 DIRTY SIGN FACE |  | Cat 2 Awaiting Action | 286162 | 600140 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 32m | NSW92-621123-429 | 2021-03-17 11:08 | CATEGORY 2 | Road Traffic Signs | Dirty Signs (DIRT) |  |  | Cat 2 Awaiting Action | 286143 | 600146 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 73m | NSW92-621123-430 | 2021-03-17 11:13 | CATEGORY 2 | Road Traffic Signs | Damaged (DAMG) | DAMAGED SIGN FACE AND POSTS |  | Cat 2 Awaiting Action | 286122 | 600182 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 334m | NSW92-621123-431 | 2021-03-17 11:14 | CATEGORY 2 | Road Traffic Signs | Damaged (DAMG) | DAMAGED ENTRANCE BOLLARD |  | Cat 2 Awaiting Action | 285971 | 600390 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 404m | NSW92-621123-432 | 2021-03-17 11:16 | CATEGORY 2 | Road Traffic Signs | Damaged (DAMG) | VARIOUS DAMAGED VERGE MARKERS |  | Cat 2 Awaiting Action | 285955 | 600458 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 568m | NSW92-621123-433 | 2021-03-17 11:17 | CATEGORY 2 | Road Traffic Signs | Physical condition of post (COPT) |  |  | Cat 2 Awaiting Action | 285949 | 600618 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 580m | NSW92-621123-434 | 2021-03-17 11:17 | CATEGORY 2 | Road Traffic Signs | Damaged (DAMG) | VARIOUS DAMAGED VERGE MARKERS |  | Cat 2 Awaiting Action | 285950 | 600630 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 977m | NSW92-621123-435 | 2021-03-17 11:18 | CATEGORY 2 | Road Traffic Signs | Damaged (DAMG) | VARIOUS DAMAGED VERGE MARKERS |  | Cat 2 Awaiting Action | 285950 | 601020 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 1053m | NSW92-621123-436 | 2021-03-17 11:19 | CATEGORY 2 | Road Traffic Signs | Damaged (DAMG) | VARIOUS DAMAGED VERGE MARKERS |  | Cat 2 Awaiting Action | 285935 | 601095 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 973m | NSW92-621123-437 | 2021-03-17 11:26 | CATEGORY 2 | Road Traffic Signs | Other (OTHR) | PARKING SIGN FACING WRONG WAY |  | Cat 2 Awaiting Action | 285950 | 601016 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 1230m | NSW92-621123-438 | 2021-03-17 11:27 | CATEGORY 2 | Road Traffic Signs | Damaged (DAMG) | VARIOUS DAMAGED/DIRTY VERGE MARKERS |  | Cat 2 Awaiting Action | 285886 | 601264 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 1274m | NSW92-621123-439 | 2021-03-17 11:27 | CATEGORY 2 | Carriageways | Bituminous surfacing fretting (BFRT) | FRETTING |  | Cat 2 Awaiting Action | 285888 | 601308 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 1552m | NSW92-621123-440 | 2021-03-17 11:28 | CATEGORY 2 | Road Traffic Signs | Damaged (DAMG) | VARIOUS DAMAGED/DIRTY VERGE MARKERS |  | Cat 2 Awaiting Action | 285991 | 601556 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 1755m | NSW92-621123-441 | 2021-03-17 11:42 | CATEGORY 2 | Carriageways | Bituminous surfacing fretting (BFRT) |  |  | Cat 2 Awaiting Action | 286057 | 601749 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 1772m | NSW92-621123-442 | 2021-03-17 11:43 | CATEGORY 2 | Road Traffic Signs | Damaged (DAMG) | VARIOUS DAMAGED/DIRTY VERGE MARKERS |  | Cat 2 Awaiting Action | 286072 | 601761 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/15 | Chainage: 2004m | NSW92-621123-443 | 2021-03-17 11:44 | CATEGORY 2 | Road Traffic Signs | Damaged (DAMG) | VARIOUS DAMAGED VERGE MARKERS |  | Cat 2 Awaiting Action | 286079 | 601990 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/29 | Chainage: 83m | NSW92-621123-444 | 2021-03-17 11:45 | CATEGORY 2 | Carriageways | Localised cracking (LOCK) |  |  | Cat 2 Awaiting Action | 286052 | 602082 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/37 |  | NSW92-621123-445 | 2021-03-17 11:48 | CATEGORY 2 | Road Traffic Signs | Damaged (DAMG) | VARIOUS DAMAGED VERGE MARKERS |  | Cat 2 Awaiting Action | 286146 | 603566 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/37 |  | NSW92-621123-446 | 2021-03-17 11:54 | CATEGORY 2 | Carriageways | Bituminous surfacing fretting (BFRT) |  |  | Cat 2 Awaiting Action | 286113 | 603512 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/37 |  | NSW92-621123-447 | 2021-03-17 11:55 | CATEGORY 2 | Carriageways | Bituminous surfacing fretting (BFRT) |  |  | Cat 2 Awaiting Action | 286136 | 603557 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/37 |  | NSW92-621123-448 | 2021-03-17 11:55 | CATEGORY 2 | Carriageways | Bituminous surfacing fretting (BFRT) |  |  | Cat 2 Awaiting Action | 286140 | 603557 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/37 |  | NSW92-621123-449 | 2021-03-17 11:57 | CATEGORY 2 | Carriageways | Bituminous surfacing fretting (BFRT) |  |  | Cat 2 Awaiting Action | 286134 | 603600 | Detailed Inspection TEMPLATE of NSW A76 Dumfries Detail Inspection Route on 10 March 2021
A76 | 13206/29 | Chainage: 33m | NSW73-624542-238019664 | 2021-03-19 11:49 | CATEGORY 1 | Carriageways | Pothole (POTH) | CAT 1 1ST TIME PERM POTHOLE | 2021-03-19 14:30 | Completed Defects | 286055 | 602033 | Safety Patrol of NSW A76 Winter Safety Patrol Route on 19 March 2021
A76 | 13206/15 | Chainage: 1755m | NSW73-624542-238019665 | 2021-03-19 11:50 | CATEGORY 1 | Carriageways | Pothole (POTH) | CAT 1 1ST TIME PERM POTHOLE | 2021-03-19 14:30 | Completed Defects | 286060 | 601747 | Safety Patrol of NSW A76 Winter Safety Patrol Route on 19 March 2021
A76 | 13206/15 | Chainage: 1753m | NSW73-624542-238019666 | 2021-03-19 11:52 | CATEGORY 1 | Carriageways | Pothole (POTH) | CAT 1 1ST TIME PERM POTHOLE | 2021-03-19 14:30 | Completed Defects | 286052 | 601748 | Safety Patrol of NSW A76 Winter Safety Patrol Route on 19 March 2021
A76 | 13206/15 | 339.35 | D-NSW21238047377 | 2021-04-08 20:49 | CATEGORY 1 | Carriageways | Debris in traffic Lane (DBTL) | 3617 - Debris from RTC | 2021-04-08 22:00 | Completed Defects | 285979 | 600399 | Control Room Defect
A76 | 13206/37 | 643 | D-NSW21238156166 | 2021-05-31 14:40 | CATEGORY 2 | Road Markings | Wear (for example erosion) (WEAR) | CAT 2 CORRODED CENTRE LINE | 2021-09-01 | Completed Defects | 286083 | 603694 | Control Room Defect
A76 | 13206/15 | Chainage: 1405m | NSW73-665762-238159378 | 2021-06-10 13:19 | CATEGORY 1 | Woodland Areas and Trees | Overhanging/overgrown (OVER) | CAT 1 OVERHANGING BRANCH | 2021-06-10 13:20 | Completed Defects | 285902 | 601439 | Safety Inspection of NSW A76 Safety Inspection Route on 10 June 2021
A76 | 13206/15 | Chainage: 1200m | NSW73-646070-4 | 2021-06-29 16:08 | CATEGORY 1 | Road Markings | Wear (for example erosion) (WEAR) | CAT 1 FADED DOUBLE SOLID CENTRE LINE | 2021-07-22 13:00 | Completed Defects | 285889 | 601234 | Visual Inspection During Darkness - Road Markings of NSW A76 Safety Inspection Route on 17 June 2021
A76 | 13206/37 | Chainage: 5m | NSW73-646070-5 | 2021-06-29 16:11 | CATEGORY 1 | Road Markings | Wear (for example erosion) (WEAR) | CAT 1 FADED DOUBLE SOLID CENTRE LINE | 2021-07-22 12:00 | Completed Defects | 286107 | 603106 | Visual Inspection During Darkness - Road Markings of NSW A76 Safety Inspection Route on 17 June 2021
A76 | 13206/15 | Chainage: 1856m | NSW73-737003-238409533 | 2021-10-07 13:29 | CATEGORY 2 | Road Traffic Signs | Damaged (DAMG) | CAT 2 DCP DAMAGED CHEVRON SIGNS |  | Cat 2 Awaiting Action | 286103 | 601840 | Safety Inspection of NSW A76 Safety Inspection Route on 07 October 2021
A76 | 13206/15 | Chainage: 1282m | NSW74-743305-238427520 | 2021-10-18 14:26 | CATEGORY 2 | Carriageways | Overhanging/overgrown (OVER) | CAT 2 OVERGROWN VEGETATION OBSCURING JUNCTION VISIBILITY 40M LENGTH |  | Cat 2 Awaiting Action | 285882 | 601316 | Safety Patrol of NSW A76 Winter Safety Patrol Route on 18 October 2021
A76 | 13206/37 | Chainage: 447m | NSW73-762375-238465789 | 2021-11-22 11:21 | CATEGORY 1 | Carriageways | Pothole VIAFIX (POTV) | CAT 1 28 DAY POTHOLE 1M X1M X45MM | 2021-11-25 12:00 | Completed Defects | 286115 | 603512 | Safety Patrol of NSW A76 Winter Safety Patrol Route on 22 November 2021
A76 | 13206/37 | Chainage: 449m | NSW73-762375-238465790 | 2021-11-22 11:24 | CATEGORY 2 | Carriageways | Patch - loss of material (fretting) (PLMT) | CAT 2 LOSS OF MATERIAL (FRETTING) 10M X 2M X 45MM +10M CONT WHITE LINE 150MM |  | Cat 2 Awaiting Action | 286110 | 603518 | Safety Patrol of NSW A76 Winter Safety Patrol Route on 22 November 2021
A76 | 13206/37 | Chainage: 583m | NSW74-764018-238466299 | 2021-11-25 12:14 | CATEGORY 1 | Carriageways | Pothole (POTH) | CAT 1 28 DAY POTHOLE 0.5M X 1M X 45MM | 2021-12-13 14:30 | Completed Defects | 286111 | 603634 | Safety Inspection of NSW A76 Safety Inspection Route on 25 November 2021
A76 | 13206/37 | Chainage: 699m | NSW74-764018-238466300 | 2021-11-25 12:18 | CATEGORY 1 | Carriageways | Pothole (POTH) | CAT 1 28 DAY POTHOLE 1M X 1M X 45MM | 2021-12-13 14:30 | Completed Defects | 286016 | 603718 | Safety Inspection of NSW A76 Safety Inspection Route on 25 November 2021
A76 | 13206/37 | Chainage: 364m | NSW73-766167-238468534 | 2021-11-29 11:43 | CATEGORY 2 | Grass, Bulbs and Wildflower Areas | Other (OTHR) | CAT 2 FALLEN TREE DEBRIS ON VERGE LENGTH X 10M |  | Cat 2 Awaiting Action | 285930 | 603540 | Safety Patrol of NSW A76 Winter Safety Patrol Route on 29 November 2021
A76 | 13206/33 | Chainage: 945m | NSW73-766167-238468535 | 2021-11-29 11:54 | CATEGORY 2 | Grass, Bulbs and Wildflower Areas | Other (OTHR) | CAT 2 FALLEN TREE DEBRIS ON VERGE LENGTH X 100M |  | Cat 2 Awaiting Action | 286053 | 603031 | Safety Patrol of NSW A76 Winter Safety Patrol Route on 29 November 2021
A76 | 13206/33 | Chainage: 58m | NSW73-766167-238468536 | 2021-11-29 12:04 | CATEGORY 2 | Grass, Bulbs and Wildflower Areas | Other (OTHR) | CAT 2 FALLEN TREE DEBRIS ON VERGE LENGTH 10M |  | Cat 2 Awaiting Action | 286021 | 602164 | Safety Patrol of NSW A76 Winter Safety Patrol Route on 29 November 2021
A76 | 13206/15 | Chainage: 1537m | NSW73-766167-238468537 | 2021-11-29 12:16 | CATEGORY 2 | Grass, Bulbs and Wildflower Areas | Other (OTHR) | CAT 2 FALLEN TREE DEBRIS ON VERGE LENGTH 25M |  | Cat 2 Awaiting Action | 285982 | 601545 | Safety Patrol of NSW A76 Winter Safety Patrol Route on 29 November 2021