## Communicating Analysis
Outcome | Drivers | Secondary Drivers | Tasks | Status | Comments
| Analysts are bold in communicating evidence, and are in the right place at the right time to be influential | Analysts are skilled in communicating to a variety of audiences | Analytical comms skills programme including: | Complete
|  |  | Induction - effective writing, presenting, IT comms skills + SG processes | Complete
|  |  | Leadership - managing comms projects, working with media, presenting to seniors | Complete
|  | We have an agreed evidence narrative for the most significant policies | Develop approach to publising evidence behind SG decisions | In progress | Have done a research study looking at a range of policy decisions and evidence behind those
|  |  | Review high level summaries of statistics | On hold | Low priority
Decision makers and influencers access and understand evidence and data about Scotland when making key decisions |  |  | Develop and deliver an 'evidence masterclass' series for policy and Ministers | On hold | Low priority
|  | Analysts are supported to be Innovative in how they communicate | Sessions to share good practice | On hold | The SPACe programme are carrying out a snapshot review of publications, which will feed into this
|  |  | Peer collaboration support available | In progress | Peer collaboration support is available through the R and User Groups, which fall under the SPACe programme's shared training remit.
|  |  | Annual communicating analysis award | In progress | Launched the 2018 award in September to cover all public bodies producing official statistics. Have Scottish Government Permanent Secretary judging finalists and UK National Statistician handing out award on finals day in December
| Systems supporting analytical products make them cost effective to deliver, have great reach, and easy to find and use | Analysts understand how effective our products are | User research on analytical web products | In progress | A user persona report has been completed as part of the SPACe programme's User Focussed Service Design workstream. The group will be presenting the personas at the Statistics Conference in November and are also working on design principles to assist with the practical application of the findings from the report.
|  |  | Develop work shadowing opportunities | In progress | Links to the Analytical comms skills programme
|  |  | Training on managing comms projects | In progress | Links to the Analytical comms skills programme
|  |  | Review of analytical twitter effectiveness | On hold | Low priority
|  | We explore ways to share knowledge and data with media organisations | Secondment to BBC - building our skills | Complete | Sessions have been held at the BBC
|  |  | Pathfinder projects getting data to wider audience through BBC | On hold | This will be progressed when the Head of Staff returns from leave
|  | IT systems are developed to make our evidence and data easier to find & use | Develop blog platorm for communicating analytical products | Complete | Blog platform available and several areas are now using it but uptake is quite low.
|  |  | Put analytical content on gov.scot | In progress | Digital Comms are leading on this. It is proving to be more complex than expected and the content is not agreed yet. However, we are working with ASDs to determine dates and create a project plan.
|  |  | All data on statistics.gov.scot inc data about Scotland from UK producers | In progress | Significant progress has been made since last Board meeting, for example, with labour market data and schools data. Putting all data on it may not be feasible as this is an unknown quantity but this it being reviewed.
|  |  | Review of support from APS | In progress | A review of the templates APS produce is ongoing

## Analytical Data Infrastructure
Outcome | Drivers | Secondary Drivers | Tasks | Status | Comments
| Efficient use of resource | Shared ways of working | Review statistical processes across SG/ISD/NRS and align where this is beneficial | On hold | This was considered as part of the SPACe programme. The programme sponsor group took a decision to focus on other workstreams and so this option is on hold.
|  |  | Review and establish common approaches to report structures | On hold | This has developed into the Common Formats workstream within SPACe, which is currently waiting for a PM to be appointed
|  | Visiblity and transparency | Development of the Analytical Data Management Platform | In progress | A beta version of the system has been released to users and data is being progressively loaded onto it. A proof of concept is currently being developed for a structured data repository, that will allow users to connect with the data regardless of the analytical tool they use.
Our systems for collecting data minimise the burden on those supplying and analysing data |  |  | Study the customer experience of the Scottish analytical data user to understand how improvements can be made to their customer journey. Endeavour to make a more seamless experience where multiple organisations are involved. | In progress | This has developed into the User Focus Service Design workstream within SPACe. In addition, there is related activity across SG (e.g. in user research) and partners (e.g. with the CivTech challenge on access to data, entering pilot soon)
| Availability of high quality, timely, relevant datat | Development of new sources of data | Data Source Review including investigating the potential of administrative data to contribute to improvement in the quality of official statistics (post 2017) | In progress | Roger gave an example of where this is happening for private sector data. He is meeting Economic Stats and Open Banking to see if we use bank data to help with economic stats
|  | The public trusts the way we handle their data | Develop public engagement approach | In progress | Progress halted due to paternity leave
|  |  | Develop understanding and compliance with new data protection regulations | In progress | Guidance for statisticians now available on Data Protection Act 2018
|  | We get best value from our investment in household surveys | Develop next steps in our survey strategy | Complete | The updated long term strategy was launched in early 2018
|  |  | Investigate move to online surveys and potential for online panels | In progress | Some early discussions have been held about what would be required.

## Statistician Development
Outcome | Drivers | Secondary Drivers | Tasks | Status | Comments
| We recruit highly competent data managers and analysts | Have a clear agreement on how we will work together to recruit and retain staff producing official statistics across the Scottish public sector | Develop shared promotional material for careers in offical statistics in Scotland | In progress | Discussions have been held with SG analysts, and agreement to seek to join up on promoting SG analyst careers gained.
|  |  | Provide an offer to graduates that is clear and extends to career progression | In progress | The possibility of a statistical branch of the SG Graduate Development Programme (GDP) has been explored, but the benefits did not justify resources required. We're looking to recruit 4 UK Fast Streamers next year as a pilot, and considering bidding for Generalist GDP staff to do placements in analytical areas.
People producing official statstics in Scotland build careers across the public sector delivering public value using data | Rewarding career pathways are available across the Scottish public sector | Identify and overcome barriers to staff moving between organisations | Explore barriers to movement of statisicians across the public sector | In progress | A recommendations report was produced in April 18 by the SPACe Programme's Mobility of People workstream. They are currently working on the feasiblity of implementing the recommendations that the Programme Board approved and a report will be produced by the end of October.
|  |  | Put in place agreements across orgs to mitigate terms/conditions differences | On hold
|  | A strong statistical community across the Scottish public sector | Develop regulations to allow a wider group of organisations to produce official statistics | In progress | Initial planning and engagement has begun.
| Learning and development opportunities exist that support career goals and business needs | Statisticians have strong technical skills | Review induction/basic training particularly around data science and communications | In progress | An induction review is in progress and improvements are being made based on feedback.
|  |  | Change how we train people on analytical software: shared basic training carried out in-house and advanced training is scheduled jointly | In progress | Joint R training has been implemented via the SPACe Programme and the workstream are currently creating a proposal for resource to support this as it moves into BAU.
|  | Statisticians develop strong leadership skills | Develop and deliver analyst leadership programme | On hold | Progress halted due to maternity leave but the intention is to explore this with other professions.

## Data Access & Governance
Outcome | Secondary Drivers | Tasks | Status | Comments
| Users know what data underpins official statistics in Scotland | Develop Scottish dataset prospectus with searchable metadata | Complete
| Outputs of non personal data are available to users on self-service basis | All data on statistics.gov.scot inc data about Scotland from UK producers | In Progress | Statistics.gov.scot went live in February 2016, with 126 datasets. As of October 2018, it holds 240 datasets, with around 25 new or updated datasets now uploaded every month. We uploaded our first management information datasets in May 2018. Open data commitments are being drafted as part of the new Open Government Action Plan. We are investigating with ISD the feasibility of a data pipeline from the NHS open data platform to statistics.gov.scot.
|  | Investigate self service tabulation products | In Progress | We have completed an analysis of the options for a statistical disclosure control tool that would enable the delivery of a flexible tabulation platform. We are considering the options and identified possible next steps, including a potential collaboration with ONS. Progress has been limited in recent months because of other priorities and the need to wait for ONS to progress their work. Resources are being put in place that will allow the work to be taken forward over the next few months.
Users can quickly and safely access data they need to make decisions and conduct further research | The public trust the way we handle their/our data and derive value from it | Programme of communications work engaging the public in use of our/their data | In Progress | Recent work includes advising the Scottish Household Survey team on publicity for the annual report, issued 04 September.
|  | Continually engage to explain how this is evolving and how changes affect what we do | On hold | Progress halted due to paternity leave
|  | Provide opportunity for the public to get involved/learn more | In Progress | Planned work includes a public Show and Tell for the Online Identity programme, scheduled for December and continuing outward facing engagement via the @scotstat twitter.
| There are efficient and effective processes supporting secondary data analysis | Speed up cycles of data linkage, and of data innovation projects | In Progress | Design of changes to the process for linking data – redesigning and recommissioning service model
|  | Clarify and communicate data access processes | Complete | Data access and approvals processes and forms were refreshed and uploaded with the coming together of the SG Data Access Panel with the Statistics PBPP.
|  | Support data sharing legislation to overcome barriers to accessing data | Complete & In Progress | The first set of regulations were passed in Scottish Parliament and in force as of 13th September however there is now appetite to lay further regulations and we have started the engagement around this.
|  | Explore other methods to overcome cultural barriers to better data sharing and data access | In Progress | Our team will be working with data suppliers to lead a conversation on use of data for statistics and research.
|  | Build skill of analysts in running data linkage projects and analysing linked data | In Progress | Provide resource to fund posts for analysing linked data (2 posts under ADRP-S). Convening the regular data linkage analysts network to share experience and learning among project leads, providing training sessions for analysts to understand the impact of changes to data protection law.
| Data from outwith Scottish statistics providers are accessed and used to enhance official statistics about Scotland | Work with external partners to identify and access new sources of data | On hold | Low priority
|  | Invite views, conduct high profile events | On hold | Low priority